## Slide 1: Next Steps
Activity | Timelines
EQA Sensitization Meeting | 17th Aug 2021
Sites enrollment in EQA portal to complete | 18 -21 Aug 2021
Panel Dispatch | 23-25 Aug 2021
Expected to reach the panel to the sites | 3-10 Sep 2021
Result submission by the sites (within 2 days of receipt of samples) | 4-14 Sep 2021 (Due Date)
Start of Analysis | 15 Sep 2021
Result EQA Feedback to sites | 3rd wk of Sep 2021
Post EQA Visits | 20-27 Sep 2021
Final report preparation and submission to CTD and States | 1st wk Oct 2021